## Slide 1: Why Monitor?
Compliance with applicable Federal requirements & performance goals are being achieved.
Prevention of fraud & waste
Early detection of inefficiencies
Ability to attain future funding
Notes: Goal

## Slide 2: Who to Monitor?
All CDBG sub recipient should be monitored once per year
Develop a Risk Assessment to determine the methods and frequency of monitoring sub recipients and programs?
Assign a point value to each sub-factor “High” “Moderate” “Low” Risk
Create a plan to match the capacity of your staff resources with the needs of sub recipient monitoring

## Slide 3: Risk Assessment Factors
• Financial Management
• Overall Management
• Satisfaction (Citizen Complaints)
• Services (Complexity of Programs)

## Slide 4: Potential Risk Factors
Financial
Rank sub recipient by the size of grant
Look at timeliness of expenditures, and completions
Program income for those that generate income
Current Audit and single Audit if applicable with unresolved finding that relates to sponsored program activity
Award size relative to sub recipient capabilities

## Slide 5: Potential Risk Factors
Management
New sub recipient or new to this type of project
New staff or vacancy in key positions
Program complexity
Submissions are not timely and/or accurate
Has not had on site Monitoring for two years

## Slide 6: Potential Risk Factors
Satisfaction
Citizen complaints
Responsiveness to complaints
History of non-compliance
National objective not met

## Slide 7: Potential Risk Factors
Services
National Citizen complaints
No response to complaints
Inadequate knowledge of CDBG rules and Regulations
Unsatisfactory performance

## Slide 8: When to monitor?
During grant performance period
Schedule an entrance conference with the program director and other personnel instrumental with financial and program administration of the award

## Slide 9: Conduct the Monitoring Review
Meet with involved staff to clarify information
Interview beneficiaries as appropriate and/or review client files
Beware of any confidentiality conflicts
Confirm project goals have been met or exceeded
Verify sub recipient is not debarred or suspended

## Slide 10: Monitoring Report
Monitoring report to sub recipient within 30 days
Written report to sub recipient within 30 days of visit
If any problems or concerns are identified ask for a timely response
Findings – corrective action
Concerns – recommended action
Be specific about what is necessary to clear any negative findings or concerns.

## Slide 11: Monitoring Response
Allow Director and/or Board Chair to respond and supply information relevant to the monitoring.
Give an opportunity to supply any missing information or clarify misunderstanding relative to review.
If corrective action is called for, begin to discuss steps that will be taken or are underway.