## MPNAHRO Annual Workplan
MPRC Annual Work Plan
Action Item/ Task | Who | When
ADMINISTRATION/ MANAGEMENT
Monthly Billing | DM/ Treasurer | 1st of each month
Maintain Member list | DM | As Needed
Request List Review from State Presidents | DM | 1x/ year: March 1
Provide Updated List to Regional Director | State Pres | 1x/year: March 31
Respond to Member Inquiries | DM | upon request
Strategic Plan/ Goals | DM/ Board | 1x/year: Feb planning mtg
Job Descriptions- Roles and Resonsibilities | DM/Board | Review 1x/year
State Dues Invoices | Treasurer | 1x/year: January
Financial Statements | Treasurer | 4-5x /year; for each Board mtg
Produce Financial Statement | Treasurer | 2 weeks prior to Board Meetings or Regional Conference
Procure, Edit and Distribute Financial Statement to Board | DM | same as above
Broadcast Notices of Elections | DM | Every two years: 60 and 20 days before annual meeting
CONFERENCES
Regional Conference
Assists the State Chapter(s) responsible for the conference in the selection of the conference site; | DM | 1x/yr: July-August
Negotiate the conference hotel contract; | DM | 1x/yr: July-August
Prepares a time-line and planning guide for the conference; | DM | 1x/yr: September-October
Prepares a conference budget for approval by the Board and Planning Committee; | DM | 1x/yr: September- October
Develop Sponsor Package for sponsors, exhibitors, advertisers | DM | 1x/yr: November
Responsible for contacting, obtaining and negotiating all sponsorships/vendors for the conference; | DM | November- June
Staffs the conference committee; | DM | Oct- June
Designs, executes and markets the conference promotional campaign; | DM | Jan- May
Produces Registration Brochure | DM | In mail 2.5 mths before conference
Designs Conference Web Page | DM | 2.5- 3 mths before conference
Produces Email Broadcast Campaign to Promote Conference | DM | Feb- May
Produces Conference Program Booklet | DM | At printer 2 weeks before conf
Handles all conference mailings and logistics including all pre-conf and on-site registration | DM | Oct- June
Develop Conference Mobile App | DM | Upon Program Completion
Attends and manages conference. | DM | During Event
National Conference | DM
Attends at least two national NAHRO conferences per year and participates on a national committee as directed by the Executive Board. | DM | March, July, October
PUBLICATIONS AND WEBSITE
Produce Legislative Agenda |  | Feb- March
Produce Conference Brochure and Program Booklet |  | (see conference)
Produce Conference Website and Registration Systems |  | (see conference)
Update MPRC Website
Update Calendar and Events | DM | 1x/month
Post Board Meeting Minutes | DM | within two weeks of meeting
Publish Job Notices | DM | as requested
Update Board List | DM | 1x/ quarter
Newsletter | DM | not currently doing one
Produce Broadcast Emails to Members as Needed | DM | as needed
BOARD, COMMITTEE AND MEETINGS
Organize, Schedule and Manage Board Meetings at each national NAHRO conference | DM
Work with President to establish meeting dates and times | DM | 1-2 months prior
Procure meeting space from National NAHRO | DM | 1-2 months prior
Communicate via broadcast email meeting info to Board | DM | 1 month prior
Handle meeting agenda and logistics | DM | 1-3 weeks prior
Attend meetings and record minutes | DM | each meeting
Organize, schedule and manage annual Board planning retreat in early February | DM | 1-2 months prior
Help select location and negotiate hotel contract | DM | 1-2 months prior
Communicate via broadcast email meeting info to Board | DM | 1 month prior
Handle meeting agenda and logistics | DM | 1-3 weeks prior
Attend meetings | DM
Presidential Support | DM | as requested
Organize Orientation Meeting for incoming Presidents | DM | every two years in October
Participate in Orientation Meeting for incoming Presidents | Reg Pres/ Sr VP; DM | every two years in October
Assists with production of BOG Report | DM | 3x/yr: March 1; July 1; Oct 1
Produce BOG Report | Reg Pres | 3x/yr: March 1; July 1; Oct 1
State Presidents Coordination
Monthly State Presidents Teleconference | DM/State Prez/ Reg Prez; Sr VP | not currently active
Sets up meeting and provides notice | DM | 2 wks prior: last thurs of mth
Agenda for meeting | DM | 1 wk prior: first thurs of mth
Minutes for meeting | DM | by 10 days after meeting
Quarterly BOG Report for President | State Prez | due March 1; Jly 1; Oct 1
Standing Committee Support | DM/Reg Prez/ VPs
Organize Orientation Meeting for incoming VPs | DM | every two years in November
Participate in Orientation meeting for incoming VPs | DM/VPs/ Reg Prez/ Sr VP | every two years in November
Assist VPs with goal setting and staying on track | DM | every two months via email or phone
Advocacy Support | DM/ Leg Net | need to discuss
Ad Hoc Committee Support | DM | as directed by Prez
MEMBER SERVICES
Manage Barbara Cook Educational Scholarship Program and National NAHRO Merit Scholalrship | DM/MS committee | TBD
Coordinate Awards with VP Members Services | DM/ VP MS | Jan- May
Provide Guidance for Awards Program at Annual Conference | DM | Jan- May
Work with VP MS to identify "Lifetime Achievement Awards" for retiring members | DM/ VP MS | Ongoing: discuss at least 1x/yr in March
Work with VP MS to market and execute the national Merit Scholarship Program | DM/ VP MS | jan-may
Promote, Manage and Execute Annual "What Home Means to Me" Poster Contest | DM | jan- june
Send out notice of contest with rules and applications to Membes | DM | january
Develop a strategy for judging posters (usally by conference attendees at annual event) | DM | jan-june
Send winning posters to National NAHRO national competition judging | DM | july
TRAINING
Assist VP Professional Development in Organizing and Promoting Periodic Training | DM/ PD | meet 1x/quarter
Promte NPDS
Broadcast Notices of Training Center Events | DM | dependent on schedule of training

## Park City Timeline
MPNAHRO June 17-19, 2019- Sherton Park City Hotel
October
23 | Planning Mtg#1- Teleconference: Review 2019 ; Committee Organization and Orientation
31 | Broadcast Announcement of Conference
31 | Workshop Request for Proposals
November
19 | Planning Meeting #2- General Sessions; Sessions; Entertainment; Theme
December
2 | Corporate & Conference Sponsor Program Outreach- email, mail, calls etc…
17 | Planning Meeting #3- General Session and Breakout Sessions Detail
January
14 | Planning Meeting #4; Registration Brochure Detail
February
3 | Session Proposal Applications due
11 | Planning Meeting #5- Registration Brochure
12 | Notify Session Proposal Applicants
21 | Registration Brochure Material Due
24 | Lead Sponsor- Deadline for Brochure Feature Ad
24-28 | Draft Registration Brochure
March
2-6 | Registration Brochure Production/ Graphics
9-13 | Registration Brochure Printer
2-13 | Develop CVENT Web Page
17 | Registration Brochure in Mail
18 | CVENT Registration Broadcast
April
14 | Planning Meeting #6- Program
May
4 | Sponsor Registration Deadline- collect ads (soft deadline #1)
4 | Awards applications deadline
4 | Scholarship application deadline
5 | Planning Meeting #7- Program
5 | Notify conference scholarship winners
14 | Early Registration Deadline
15 | Session Summary Sheets and Speaker Registration Forms Due
18 | Menu Selectiions to Hotel
18 | Confirm Sponsored Events with Sponsors
18 | Sponsor/ Vendor Ads due
18 | Order deadline for registration bags, name badges, lanyards, note pads etc…
18 | Sponsor Registration Deadline- collect ads (hard deadline)
18-22 | Draft Conference Program
20-22 | Conference Program Draft to Committee for Edits
22 | Session Room Assignment to Conference Center
25-29 | Program Layout Graphics
27 | Hotel block release date
29 | Awards Order (plagues and ribbons) due to Arrowhead
June
1-5 | Print Program
1-5 | Develop Mobile App
1 | Notify conference awards winners
1 | Vendor registration/ badge forms due
1 | Do non-registered speaker, vendor and guest list
1 | Copy all materials for session packets, evals, signs
1 | Collate session packets
1 | Create signs (session, speaker, events, boxes, podiums)
1 | Create vendor card, session & conference evaluations, and meal tickets
1 | Prep for annual meeting
1 | Audio-visual list for Hotel
1 | Vendor layout and electrical to Hotel
1 | Memo out to procure LCD's and Laptops
5 | Conference program back from printer
5 | Conference Flow to President and other VIPs
8 | Review Banquet Event Orders
8 | Revise/ update conference budget
8 | Pick-up awards plaques, ribbons, programs
11 | Notify hotel of food guarantees
12 | Printout registration badges for participants
16 | Meet hotel staff
16 | Early Registration Begins
16 | Volunteers collate registration packets

## CoNAHRO Annual Workplan
CoNAHRO Annual Work Plan |  |  |  |  | Legand: | Requires Further discussion with Dave and transition committee
Brea will assume as part of her new role
Outsource to 3rd Party Event Planner
Action Item/ Task | Current Owner | Future Owner | When | Status | Technology or 3rd Party Assistance | Volunteer Executive Assist - Staff time donated by JHCA
ADMINISTRATION/ MANAGEMENT | [5 empty] | Registration and Annual Conference Coordinator Chair
Monthly Billing | DM/ Treasurer | Brea Gilchrist | 1st of each month |  | Excel Spreadsheet | Duties include: Dave's retainer, adminstrative duties paid by Colorado NAHRO credit card, reimbursed to Dave, lunch, etc. bills to pay i.e. invoices to be paid on behalf of CONAHRO, submitted once a month to treasuer. Certain invoices are on auto payment and show up on credit card i.e. zoom. Need one point of contact to absorb. Brea can start at this person and transition later as needed.
Maintain Member list | DM | Brea Gilchrist | As Needed |  | ACT
Respond to Member Inquiries | DM | Brea Gilchrist | upon request |  | Outlook/ Telephone
Strategic Plan/ Goals | DM/ Board | Brea Gilchrist | upon Board request
Job Descriptions- Roles and Responsibilities | DM/Board | Brea Gilchrist | Review 1x/year
Dues Invoices | Treasurer | Brea Gilchrist | 1st quarter |  |  | Ensures membership list is upated, mail merge so each member is invoiced, print the invoice, label and mail. Explore electronic software to automate. Currently done annually - 1st quarter ideally January
Financial Statements | Treasurer | Brea Gilchrist | for each Board mtg
Produce Financial Statement | Treasurer | Treasurer | 2 weeks prior to Board Meetings or Annual Conference |  |  | with review by the admn function. Review by president, VP and treasurer prior to board distribution
Procure, Edit and Distribute Financial Statement to Board | DM | Executive Assistant Volunteer | same as above
Broadcast Notices of Elections | DM | Brea Gilchrist | Every two years: see bylaws for details |  | Constant Contact
Manage Election Voting and Tabulate Results | DM | Brea Gilchrist | Every two years: see bylaws for details |  | Constant Contact/ Survey Monkey
CONFERENCES
Annual Conference
Work with Board to Select Site | DM | TBD | 1x/yr: June-August | done | To be covered by volunteer Coordinator Chair
Negotiate the conference hotel contract; | DM | 2019 planning complete confirm with DM | 1x/yr: June-August | done
Prepares a time-line and planning guide for the conference; | DM | 2019 planning complete confirm with DM | 1x/yr: September-October | done
Prepares a conference budget for approval by the Board; | DM | to be completed by Dave prior to transition | 1x/yr: September- October | 2019-11-15
Develop Sponsor Package for sponsors, exhibitors, advertisers | DM | Initial list prepared by DM to finalize by BG | 1x/yr: November | 2019-11-08
Responsible for contacting, obtaining and negotiating all sponsorships/vendors for the conference; | DM | Brea Gilchrist | Jan- May
Staffs the conference committee; | DM | Annual Conference Coordinator Chair | Oct- June
Designs, executes and markets the conference promotional campaign: | DM | Brea Gilchrist | Jan- May
Produces Registration Brochure | DM | Brea Gilchrist | In mail 2.5 mths before conference |  | Dave / Char Campbell for graphics/ Center Copy Printing
Designs Conference Web Page | DM | Brea Gilchrist | 2.5- 3 mths before conference |  | Dave designs on CVENT
Produces Email Broadcast Campaign to Promote Conference | DM | Brea Gilchrist | Feb- May |  | Constant Contact
Produces Conference Program Booklet | DM | Brea Gilchrist | At printer 2 weeks before conf |  | Dave / Char Campbell for graphics
Handles all conference mailings and logistics including all pre-conf and on-site registration | DM | Annual Conference Coordinator Chair | Oct- June |  | CVENT
Orders all conference materials (copys, signs, bags, pads, pens, awards etc…) | DM | Annual Conference Coordinator Chair | April- May |  | Kinkos (copies and signs), 4imprint (bags, pens), Name Badge Productions (name badges), personalized Paper Source (note pads), Arrowhead Awards (awards)
Develop Conference Mobile App | DM | Brea Gilchrist | Upon Program Completion |  | YAPP
Attends and manages conference | DM | Annual Conference Coordinator Chair | During Event
National Conference
Attends at least two national NAHRO conferences per year and participates on a national committee as directed by the Executive Board. | DM | NA - TBD if warranted | March, July, October
PUBLICATIONS AND WEBSITE
Produce Legislative Agenda | DM | Brea Gilchrist | Feb- March |  | Dave / Char Campbell for graphics
Produce Conference Brochure and Program Booklet |  |  | (see conference) |  | Dave / Char Campbell for graphics
Produce Conference Website and Registration Systems |  |  | (see conference) |  | CVENT
Update Website |  |  |  |  | Weebly
Update Calendar and Events | DM | Brea Gilchrist | 1x/month
Post Board Meeting Minutes | DM | Brea Gilchrist | within two weeks of meeting
Publish Job Notices | DM | Brea Gilchrist | as requested
Update Board List | DM | Brea Gilchrist | 1x/ quarter
Newsletter | DM | Brea Gilchrist | not currently doing one
Produce Broadcast Emails to Members as Needed | DM | Brea Gilchrist | as needed |  | ACT/ Constant Contact
BOARD & COMMITTEE SUPPORT
Organize, Schedule and Manage all Board Meetings as scheduled by President | DM | Executive Assistant Volunteer
Work with President to establish meeting dates and times | DM | Executive Assistant Volunteer | 1-2 months prior |  | Doodle
Procure meeting space | DM | Executive Assistant Volunteer | 1-2 months prior
Communicate via broadcast email meeting info to Board | DM | Executive Assistant Volunteer | 1 month prior |  | ACT/ Outlook
Handle meeting agenda and logistics | DM | Executive Assistant Volunteer | 1-3 weeks prior
Attend meetings and record minutes | DM | Executive Assistant Volunteer | each meeting
Presidential Support | DM | Brea Gilchrist | as Requested
Standing Committee Support | DM/ Prez/ VPs | Executive Assistant Volunteer
Organize Orientation Meeting for incoming VPs | DM | Executive Assistant Volunteer | every two years in November
Participate in Orientation meeting for incoming VPs | DM/ Prez/ VPs | Executive Assistant Volunteer | every two years in November
Assist VPs with goal setting and staying on track | DM | Executive Assistant Volunteer | every two months via email or phone
Advocacy Support | DM/ Leg Net | Brea Gilchrist | need to discuss
Ad Hoc Committee Support | DM | Executive Assistant Volunteer | as directed by Prez
MEMBER SERVICES
Manage Educational Scholarship Program and National NAHRO Merit Scholalrship | DM/MS committee | TBD | TBD
Coordinate Awards with VP Members Services | DM/ VP MS | Brea Gilchrist | Jan- May
Provide Guidance for Awards Program at Annual Conference | DM | Brea Gilchrist | Jan- May
Work with VP MS to identify "Lifetime Achievement Awards" for retiring members | DM/ VP MS | Brea Gilchrist | Ongoing: discuss at least 1x/yr in March
Work with VP MS to market and execute the national Merit Scholarship Program | DM/ VP MS | Brea Gilchrist | jan- may
Procure physical awards as needed | DM | Brea Gilchrist | may |  | Arrowhead Awards
Promote, Manage and Execute Annual "What Home Means to Me" Poster Contest | DM | Annual Conference Coordinator Chair | jan-may |  | ACT/ Constant Contact | housing authorities communicate with the schools, after submission they go to thes sponsoring agencies,
Send out notice of contest with rules and applications to Membes | DM | Annual Conference Coordinator Chair | January
Develop a strategy for judging posters (usually by conference attendees at annual event) | DM | Annual Conference Coordinator Chair | jan-june
Send winning posters to the Region for national competition judging | DM | Annual Conference Coordinator Chair | June
TRAINING
Assist VP Professional Development in Organizing and Promoting Periodic Training | DM/ PD | Brea Gilchrist | meet 1x/quarter
Promte NPDS
Broadcast Notices of Training Center Events | DM | Brea Gilchrist | dependent on schedule of training |  | Constant Contact

## Vail Timeline
CoNAHRO May 11-15, 2020- Vail Marriott Resort Hotel
October
22 | Planning Mtg#1- Teleconference: Review 2019 ; Committee Organization and Orientation
30 | Broadcast Announcement of Conference
30 | Workshop Request for Proposals
November
8 | Corporate & Conference Sponsor Program Outreach- email, mail, calls etc…
13 | CO. Planning Meeting #2- General Sessions; Sessions; Entertainment; Theme
December
9 | Session Proposal Applications due
18 | CO Planning Meeting #3- General Session and Breakout Sessions Detail
20 | Notify Session Proposal Applicants
January
8 | Planning Meeting #4; Registration Brochure Detail
15 | Registration Brochure Material Due
20-24 | Draft Registration Brochure
24 | Diamond Sponsor- Deadline for Brochure Feature Ad
27-31 | Registration Brochure Production/ Graphics
27-31 | Develop CVENT Web Page
February
3-7 | Registration Brochure Printer
10 | Registration Brochure in Mail
12 | CVENT Registration Broadcast
19 | Planning Meeting #5-Teleconference: If necessary
March
11 | Planning Meeting #6- Program
19 | Draft and Email Exhibitor Logistics
April
1 | Sponsor Registration Deadline- collect ads (soft deadline #1)
1 | Planning Meeting #6- Program (final meeting)
6 | Awards applications deadline
6 | Scholarship application deadline
9 | Notify conference scholarship winners
10 | Menu Selectiions to Hotel
10 | Session Room Assignment to Conference Center
10 | Session Summary Sheets and Speaker Registration Forms Due
10 | Early Conference Registration deadline
10 | Confirm Sponsored Events with Sponsors
10 | Sponsor/ Vendor Ads due
10 | Sponsor Registration Deadline- collect ads (hard deadline)
10 | Order deadline for registration bags, name badges, lanyards, note pads etc…
13-17 | Draft Conference Program
17 | Hotel block release date
15-17 | Conference Program Draft to Committee for Edits
20-24 | Program Layout Graphics
22 | Notify conference awards winners
22 | Vendor registration/ badge forms due
22 | Awards Order (plagues and ribbons) due to Arrowhead
27-1 | Print Program
27-1 | Develop Mobile App
May
1 | Do non-registered speaker, vendor and guest list
1 | Copy all materials for session packets, evals, signs
1 | Conference Flow to President and other VIPs
1 | Collate session packets
1 | Create signs (session, speaker, events, boxes, podiums)
1 | Create vendor card, session & conference evaluations, and meal tickets
1 | Prep for annual meeting
1 | Audio-visual list for Hotel
1 | Vendor layout and electrical to Hotel
1 | Memo out to procure LCD's and Laptops
1 | Conference program back from printer
4 | Review Banquet Event Orders
4 | Revise/ update conference budget
4 | Pick-up awards plaques, ribbons, programs
6 | Printout registration badges for participants
6 | Notify hotel of food guarantees
12 | Meet hotel staff
12 | Early Registration Begins
12 | Volunteers collate registration packets